## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: Cyber Security
INTERN NAME: Anish Akhilesh Gupta
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2026-09-15
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | Web Service Open to Malicious Attacks
PROJECT ID | IP-11783
INTERN NAME | Anish Akhilesh Gupta
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
This Test Plan describes how the security audit of giftacareer.in was carried out and verified, using Nmap, Nikto and OWASP ZAP. Testing was performed from a Kali Linux environment against the authorised hosted instance only, following a staged approach: network/service scanning, server misconfiguration scanning, then application-layer scanning. Each checklist item from the Problem Statement is mapped to at least one test case; results are recorded in the Traceability Matrix with severity and evidence file references.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
Network/service: open ports, service versions, OS fingerprint, SSL/TLS certificate and cipher strength, HTTP security headers, HTTP methods, known CVEs, backup/config exposure, WAF presence, DoS readiness. Web server: outdated software/banners, missing headers, directory indexing, default/interesting files (Nikto). Application: SQL injection, XSS, insecure cookies, clickjacking, spidered site map (OWASP ZAP). Utility: steganography encode/decode correctness.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
Brute-force login testing, DoS/DDoS flood attacks, penetration testing of any asset other than the given hosted instance (including the external Bitrix24 redirect target), and any testing after the Findings Document is submitted.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
- Verify the site's security posture against the Problem Statement's audit checklist. - Identify any missing security headers, risky HTTP methods, or exposed backup/config files. - Confirm TLS/SSL configuration strength. - Identify and fix any defects in the steganography utility before submission. - Achieve 100% coverage of the Problem Statement's audit checklist items.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
- Security Tester: Anish Akhilesh Gupta - plans and executes all scans, records findings. - Test Manager: Harshada Topale (Project Manager) - reviews scope and results. - Developer: Anish Akhilesh Gupta - builds and fixes the steganography utility. - Configuration Manager: Anish Akhilesh Gupta - maintains tool output files and scripts. - Installation Team: Anish Akhilesh Gupta - sets up the Kali Linux/tool environment.
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
A staged (waterfall-style) methodology is used: network scanning first (broadest layer), then server-level scanning, then application-level scanning, because each stage's findings (e.g. detected server software) inform where to look more closely in the next stage. Test cases are derived directly from the Problem Statement's audit checklist.
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
Black-box security testing of a live, authorised web asset (System Testing at the network, server and application layers), supported by non-destructive automated scans and limited manual verification of selected findings (for example, confirming header values with curl).
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
Each finding is logged with a severity (High/Medium/Low/Informational). High-severity items (e.g. exploitable injection) would be reported immediately and retested if fixed during the window; Medium items (e.g. missing security headers) are documented with a suggested patch; Low/Informational items are listed for completeness. No fixes were applied to the target itself, as it is a third-party-managed asset - all remediation is recommended to the owner.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
Testing is complete when: every checklist item in the Problem Statement has at least one corresponding test case and result; Nmap, Nikto and ZAP scans have all been run to completion; the steganography utility correctly encodes and decodes the required message; and all findings are recorded in the Traceability Matrix with evidence.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
Test Plan; Traceability Matrix with actual results; raw scan output files (Nmap .txt/.xml/.gnmap, Nikto .txt/.html, ZAP .html/.pdf export); Findings summary with screenshots in the Project Report; steganography test evidence (encoded image + decoded message output).
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
- Nmap 7.95 (network/service/vulnerability scripts) - Nikto 2.5.0 (web-server scanner) - OWASP ZAP (application scanner) - curl (manual header verification) - Python 3 + Pillow (steganography) - Screenshot tool for evidence capture
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
- Kali Linux (VirtualBox) or native tool installs on Windows/Linux - Stable internet connection to the authorised hosted instance - Target: giftacareer.in (hosted instance only) - No test accounts were required; all testing was unauthenticated/black-box
ADDITIONAL COMMENTS
Testing was performed on 15-Oct-2026. All scans were run against the live, authorised hosted instance; no synthetic/local copy of the site was used.
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Host discovery & port scan | Confirm target reachable; identify open ports (Nmap -Pn, -sV -sC) | 2026-09-15 | 2026-09-19 | Anish Akhilesh Gupta | COMPLETED
SSL/TLS certificate & cipher check | Verify certificate validity and cipher strength (Nmap ssl-cert, ssl-enum-ciphers) | 2026-09-17 | 2026-09-22 | Anish Akhilesh Gupta | COMPLETED
HTTP security headers check | Check HSTS, X-Frame-Options, X-Content-Type-Options, CSP (Nmap http-security-headers, Nikto) | 2026-09-19 | 2026-09-25 | Anish Akhilesh Gupta | COMPLETED
HTTP methods check | Check for risky methods: PUT/DELETE/TRACE (Nmap http-methods) | 2026-09-21 | 2026-09-28 | Anish Akhilesh Gupta | COMPLETED
Known CVE / vulnerability scripts | Match detected service versions against known CVEs (Nmap --script vuln) | 2026-09-23 | 2026-10-01 | Anish Akhilesh Gupta | COMPLETED
Backup/config file & directory exposure | Check for exposed backups/admin paths (Nmap http-enum, http-backup-finder) | 2026-09-25 | 2026-10-04 | Anish Akhilesh Gupta | COMPLETED
WAF detection | Detect presence of a Web Application Firewall (Nmap http-waf-detect; Nikto anomalous header) | 2026-09-27 | 2026-10-07 | Anish Akhilesh Gupta | COMPLETED
DoS readiness check (non-flooding) | Check Slowloris-style readiness without flooding (Nmap http-slowloris-check) | 2026-10-07 | 2026-10-09 | Anish Akhilesh Gupta | COMPLETED
Full Nikto scan (HTTPS) | Run complete default Nikto checks over HTTPS | 2026-10-09 | 2026-10-11 | Anish Akhilesh Gupta | COMPLETED
Nikto scan (HTTP, port 80) | Check HTTP-to-HTTPS redirect behaviour and plaintext exposure | 2026-10-11 | 2026-10-13 | Anish Akhilesh Gupta | COMPLETED
OWASP ZAP spider & active scan | Crawl and actively test for SQLi, XSS, insecure cookies, clickjacking | 2026-10-13 | 2026-10-15 | Anish Akhilesh Gupta | COMPLETED
Steganography encode/decode test | Encode the required message into an image and verify correct decoding | 2026-10-15 | 2026-10-17 | Anish Akhilesh Gupta | COMPLETED