## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: Cyber Security
INTERN NAME: Anish Akhilesh Gupta
PROJECT NAME: Web Service Open to Malicious Attacks
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2026-09-15
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Web Service Open to Malicious Attacks |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IP-11783
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2026-09-15 | Started the internship deliverables late: only about 7 days remained before the 17-Oct-2026 submission for a 120-hour internship. | Time/Schedule management | Yes | Start from week 1, plan backwards from the deadline and set weekly milestones. | Prepared a day-wise plan and prioritised the three core tools (Nmap, Nikto, ZAP) plus the steganography utility over a broader document-heavy scope. | Anish Akhilesh Gupta | RESOLVED | Project Manager informed about the compressed timeline.
2 | 2026-10-05 | Nikto's full HTTPS scan took close to 12 minutes and returned many low-value 'error' lines alongside real findings. | Tooling/efficiency | No | Use -maxtime to cap long scans against a tight deadline, and filter output for '+' finding lines first. | Focused report-writing on the '+' finding lines; noted scan duration in the Test Plan for repeatability. | Anish Akhilesh Gupta | RESOLVED | Reduced redundant scans (dropped repeat -Tuning runs already covered by the full scan).
3 | 2026-10-15 | The target's WAF responded to scanner probes on random/non-existent paths with a distinctive 'wafrule' header. | Technical/Security | No | When an unexpected custom header appears on a scan, treat it as a signal (e.g. WAF presence) rather than noise. | Logged WAF detection as a positive finding rather than discarding it as an anomaly. | Anish Akhilesh Gupta | RESOLVED | Cross-checking unusual headers against multiple tools confirmed the WAF's presence.