## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Web Service Open to Malicious Attacks (Security Audit of giftacareer.in) Intern ID / Project ID: IP-11783
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-09-15
EXPECTED COMPLETION DATE | 2026-10-17
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To perform a complete, authorised security audit of the hosted web service at giftacareer.in covering network, server and application layers, using Nmap, Nikto and OWASP ZAP, and to document discovered vulnerabilities, exploits attempted, and suggested patches/improvements in a Findings Document, along with a steganography utility that hides and recovers the text "Cloud Counselage Internship Program" inside an image.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Web services open to the internet are a potential target of malicious actors, with motives ranging from service disruption to data theft; cybercrime was projected by Cybercrime Magazine to cost the world USD 10.5 trillion annually by 2025. It is essential for Cloud Counselage to ensure that its web assets, such as giftacareer.in, are adequately protected. A structured, tool-based audit is low-cost (open-source tools only) and gives management concrete, actionable findings. Alternatives considered: (1) no audit - rejected as it leaves risk unknown; (2) hire a paid penetration-testing firm - rejected due to cost and timeline; (3) intern-led audit using free tools under strict scope rules - selected.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | 1. Complete reconnaissance and port/service scanning of giftacareer.in with Nmap, covering SSL/TLS, security headers, HTTP methods, backups and known CVEs. 2. Complete a full Nikto web-server scan covering both HTTP and HTTPS. 3. Complete an OWASP ZAP spider and active scan of the site and export a findings report. 4. Deliver a working steganography encoder/decoder proving the message is hidden and recoverable. 5. Document every finding with severity and a suggested patch/improvement in the Findings Document. 6. Complete all deliverables by 16-Oct-2026 (submission deadline 17-Oct-2026), using zero-cost open-source tools only, with no brute-force or DoS/DDoS attacks performed.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | 1. Project Charter 2. Requirement Elicitation Questionnaire 3. Software Requirement Specification (SRS) 4. Work Breakdown Structure (WBS) 5. Project Schedule 6. RAID Log 7. Software Design Specification (SDS) 8. Coding Standards document 9. Test Plan 10. Traceability Matrix with test results 11. Nmap / Nikto / OWASP ZAP scan outputs and steganography program (encode.py, decode.py) 12. Lessons Learnt Log 13. Project / Findings Report 14. Project overview video (3-5 minutes)
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | - Reconnaissance and port/service scanning of the hosted instance (Nmap) - SSL/TLS, HTTP security-header, HTTP-methods and known-CVE checks - Web-server misconfiguration scanning (Nikto) - Application-layer vulnerability scanning: SQLi, XSS, insecure cookies, clickjacking (OWASP ZAP) - Documentation of all vulnerabilities found, tools/approach used, and suggested patches - Steganography utility to hide and recover a text message in an image
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | - Brute-force login attacks of any kind - DoS/DDoS flood attacks (only non-flooding readiness checks were performed) - Testing of any asset other than the given hosted instance of giftacareer.in - Any testing after the Findings Document is submitted - Formal penetration-testing certification or a legal compliance audit
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 resource: Anish Akhilesh Gupta (Intern - tester, analyst and documenter), guided by Project Manager Harshada Topale.
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Laptop/PC able to run Kali Linux (or Nmap, Nikto, OWASP ZAP installed natively), internet connection, Python 3 with Pillow, mentor/Project Manager guidance, and the Cloud Counselage live-project workflow portal.
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | No monetary cost - only free/open-source tools are used (Estimated Cost: N.A.). Effort: approximately 30 hours of intern effort planned between 10-Oct-2026 and 16-Oct-2026.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Tushar Topale (Project Sponsor), Cloud Counselage Pvt. Ltd.
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | - Tushar Topale - Project Sponsor - Harshada Topale - Project Manager - Anish Akhilesh Gupta - Intern / Security Tester - Cloud Counselage Pvt. Ltd. management - asset owner - CC-GAC Foundation / Industry Academia Community team
END CUSTOMER (Mention the client name.) | Cloud Counselage Pvt. Ltd. (asset: giftacareer.in)
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | 1. Very short timeline (about 7 days) to complete scanning, the steganography program and 12 documents (High). 2. Accidentally exceeding the authorised scope (e.g. scanning a redirected third-party domain) (Medium). 3. Automated scan tools being blocked or rate-limited by the target's WAF, reducing finding depth (Medium). 4. Limited intern availability due to other commitments (Medium). 5. Misreading a scan result and reporting a false positive (Low).
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | 1. Testing is authorised only on the hosted instance at giftacareer.in, as stated in the Problem Statement. 2. The Kali Linux environment with Nmap, Nikto and OWASP ZAP is sufficient; no additional paid tools are required. 3. The site's redirect to an external Bitrix24-hosted page is noted but not tested, as it is outside the authorised asset. 4. The Project Manager will provide feedback on scope and deliverables when requested.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | 1. Fixed submission deadline: 17-Oct-2026 (work completed by 16-Oct-2026). 2. Individual project; one resource only. 3. Only open-source / free tools can be used (no budget). 4. No brute-force and no DoS/DDoS attacks permitted. 5. Testing limited strictly to the given hosted instance; no local download/replication of the site.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 2026-09-15
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 2026-09-19
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 2026-09-23
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 2026-09-27
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 2026-10-13
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 2026-10-15
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 2026-10-17