## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Anish Akhilesh Gupta
Document Created On: | 10-Oct-2026
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## Project Schedule
IAC Internship Program 2026 - Cyber Security Project Schedule - Web Service Open to Malicious Attacks (Intern ID: IP-11783)
|  | PROJECT START DATE | 2026-09-15 | (Enter the date you started working on your project)
|  | Display Week Sr No | 1 | [10 empty] | 2026-09-14 | [6 empty] | 2026-09-21 | [6 empty] | 2026-09-28 | [6 empty] | 2026-10-05 | [6 empty] | 2026-10-12 | [6 empty] | 2026-10-19 | [6 empty] | 2026-10-26 | [6 empty] | 2026-11-02 | [6 empty] | 2026-11-09
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | time axis 2026-09-14 to 2026-11-15
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2026-09-14 to 2026-11-15
1 | Initiation & Requirement Gathering | [8 empty] | 16.5 | Completed | 100
1.1 |  | Project Charter |  |  |  | Anish Gupta | 2026-09-15 | 2026-09-17 |  | 5 | Completed | 100
1.2 |  | Requirement Elicitation Questionnaire |  |  |  | Anish Gupta | 2026-09-17 | 2026-09-19 |  | 5 | Completed | 100
1.3 |  | Software Requirement Specification (SRS) |  |  | 1.1, 1.2 | Anish Gupta | 2026-09-19 | 2026-09-21 |  | 6.5 | Completed | 100 | Milestone 1
2 | Planning | [8 empty] | 10.5 | Completed | 100
2.1 |  | Work Breakdown Structure (WBS) |  |  | 1.3 | Anish Gupta | 2026-09-22 | 2026-09-25 |  | 3 | Completed | 100
2.2 |  | Project Schedule |  |  | 2.1 | Anish Gupta | 2026-09-25 | 2026-09-28 |  | 4.5 | Completed | 100
2.3 |  | RAID Log |  |  | 1.3 | Anish Gupta | 2026-09-28 | 2026-10-01 |  | 3 | Completed | 100 | Milestone 2
3 | Design | [8 empty] | 21.5 | Completed | 100
3.1 |  | Research: Nmap/Nikto/ZAP scripts, scope rules, stego approach |  |  | 1.3 | Anish Gupta | 2026-10-01 | 2026-10-02 |  | 6.5 | Completed | 100
3.2 |  | Software Design Specification (test workflow design) |  |  | 3.1 | Anish Gupta | 2026-10-02 | 2026-10-03 |  | 6.5 | Completed | 100
3.3 |  | Coding Standards document (for stego script) |  |  | 3.2 | Anish Gupta | 2026-10-03 | 2026-10-04 |  | 4 | Completed | 100
3.4 |  | Test Plan |  |  | 1.3 | Anish Gupta | 2026-10-04 | 2026-10-05 |  | 4.5 | Completed | 100 | Milestone 3
4 | Development / Testing Execution | [8 empty] | 43.5 | Completed | 100
4.1 |  | Environment setup: Kali Linux / native tools (Nmap, Nikto, ZAP) |  |  | 3.2 | Anish Gupta | 2026-10-04 | 2026-10-04 |  | 6.5 | Completed | 100
4.2 |  | Nmap reconnaissance, port/service, SSL/TLS, header & vuln scans |  |  | 4.1 | Anish Gupta | 2026-10-05 | 2026-10-05 |  | 9 | Completed | 100
4.3 |  | Nikto full scan (HTTPS and HTTP) |  |  | 4.2 | Anish Gupta | 2026-10-06 | 2026-10-06 |  | 9 | Completed | 100
4.4 |  | OWASP ZAP spider and active scan |  |  | 4.2 | Anish Gupta | 2026-10-07 | 2026-10-07 |  | 10 | Completed | 100
4.5 |  | Steganography encode/decode script development & testing |  |  | 3.3 | Anish Gupta | 2026-10-08 | 2026-10-08 |  | 9 | Completed | 100 | Milestone 4
5 | Findings & Traceability | [8 empty] | 12 | Completed | 100
5.1 |  | Consolidate findings; update Traceability Matrix with results |  |  | 4.2, 4.3, 4.4 | Anish Gupta | 2026-10-08 | 2026-10-09 |  | 8 | Completed | 100
5.2 |  | Capture screenshots and evidence for the report and video |  |  | 5.1 | Anish Gupta | 2026-10-09 | 2026-10-10 |  | 4 | Completed | 100 | Milestone 5
6 | Reporting | [8 empty] | 8 | Completed | 100
6.1 |  | Write Findings/Project Report (approach, tools, vulnerabilities, patches) |  |  | 5.1 | Anish Gupta | 2026-10-11 | 2026-10-11 |  | 8 | Completed | 100 | Milestone 6
7 | Closure | [8 empty] | 14 | Completed | 100
7.1 |  | Lessons Learnt Log |  |  | 6.1 | Anish Gupta | 2026-10-13 | 2026-10-14 |  | 2 | Completed | 100
7.2 |  | Project overview video (3-5 minutes) |  |  | 6.1 | Anish Gupta | 2026-10-15 | 2026-10-16 |  | 8 | Completed | 100
7.3 |  | Final review, packaging of files and submission |  |  | 7.1, 7.2 | Anish Gupta | 2026-10-16 | 2026-10-17 |  | 4 | Completed | 100 | Milestone 7

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Job Cloud |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE
PROJECT START DATE | 2020-01-01
PROJECT END DATE | 2020-01-04
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.2 Baseline project plan |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2020-12-01 | 20/1/2020 | 8 | COMPLETED
| 3.2 Build |  | 22/1/2020 | 22/3/2020 | 59 | IN PROGRESS
| 3.2.1 Features |  | 22/1/2020 | 31/1/2020 | 9
Registration of candidate and employer
Login for candidate and employer
| Home page layout |  | 2020-01-02 | 2020-10-02 | 10
Navigation bar with logo
Home
Jobs
| Candidates |  | 2020-11-02 | 15/2/2020 | 5
List of candidates with information
| Employer |  | 16/2/2020 | 21/2/2020 | 5
List of employers with information
Advance search bar
Keyoword
Upload resume
Job categories
| Job listing/ Job result page |  | 22/2/2020 | 26/2/2020 | 4
Employer name
Job category & type information
Date & location
Favorite
Apply filter & sort
| Apply for job/ Jobs tag |  | 26/2/2020 | 29/2/2020 | 3
Employer information
Deadline of application
Job details
Job description
Role
Required skills
| Footer |  | 2020-01-03 | 2020-09-03 | 8
Quick links for candidate & employer
Legal and company information
Social media follow
| Profile |  | 2020-10-03 | 15/3/2020 | 5
Dashboard
Job alerts
Applied jobs/Posted jobs
Favorite jobs/candidates
Basic information of candidate/employer
| Post job |  | 16/3/2020 | 22/3/2020 | 7
Job title and desciption
Job category and type
Required skills and application deadline
Salary and qualification
Location
| 3.3 Testing |  | 25/03/2020 | 31/3/2020 | 6
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2020-01-04 | 2020-01-04 | 1