## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 5 | 1 | 1 | 0 | 1 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Web Service Open to Malicious Attacks |  | Project Id: | IP-11783 | Project Manager: | Harshada Topale |  |  | Assumption | 3 | 0 | 0 | 0 | 2 | 0
[10 empty] | Issue | 2 | 1 | 1 | 0 | 0 | 0
| DOCUMENT VERSION: | 1.0 |  | Last Updated date: | 2026-09-15 | Project Team Lead: | Anish Akhilesh Gupta |  |  | Dependency | 3 | 0 | 0 | 1 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 13 |  |  |  |  | 8
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Very short timeline (about 7 days) to complete scanning, the steganography program and 12 documents. | Incomplete testing or documentation; risk of missing the 17-Oct-2026 deadline. | Prioritise the three core scans and the Findings Document first; time-cap long-running scans; submit with a one-day buffer. | Anish Akhilesh Gupta | Critical | 100 | Open | Risk
2 | Risk | Accidentally testing outside the authorised scope (e.g. the external Bitrix24 redirect target). | Policy violation; testing on an asset not owned by Cloud Counselage. | Confirmed the authorised hostname before scanning; noted the redirect in the report without testing the redirected domain. | Anish Akhilesh Gupta | High | 60 | Closed | Assumption
3 | Risk | Target's WAF (observed via the 'wafrule' response header during Nikto scanning) blocking or limiting automated scans. | Some vulnerabilities may go undetected. | Documented the WAF detection itself as a positive finding; relied on three different tools to cross-check coverage. | Anish Akhilesh Gupta | Medium | 40 | Open | Issue
4 | Risk | Limited availability of the intern due to other commitments. | Fewer working hours; delay in milestones. | Block fixed daily work slots; prioritise mandatory deliverables; inform the Project Manager early. | Anish Akhilesh Gupta | High | 48 | Open | Dependency
5 | Risk | A scan result is misread and reported as a false positive. | Incorrect findings reduce report credibility. | Cross-check every notable finding across at least two tools before including it in the report. | Anish Akhilesh Gupta | Low | 12 | Open
6 | Assumption | Formal authorisation exists to test the hosted instance of giftacareer.in as stated in the Problem Statement. | If authorisation is narrower than assumed, scope must be reduced. | Testing was limited strictly to the stated hostname throughout. | Anish Akhilesh Gupta | Low |  | Open | Open
7 | Assumption | The Kali Linux environment with Nmap, Nikto and OWASP ZAP is sufficient for the audit. | If additional tools are required, extra setup time is needed. | All required tools were confirmed installed and working before scanning began. | Anish Akhilesh Gupta | Low |  | Closed | Closed
8 | Assumption | No brute-force or DoS/DDoS attacks are to be performed, per the Problem Statement. | Some vulnerability classes (e.g. weak-password accounts) cannot be confirmed. | Documented this as an explicit testing boundary in the SRS and Findings Document. | Anish Akhilesh Gupta | Low |  | Open
9 | Issue | Late start - only about 7 days remained before the 17-Oct-2026 submission for a 120-hour internship. | Compressed schedule; fewer hours than the 120-hour target; no buffer for rework. | Informed the Project Manager; reduced scope to the three core tools plus the steganography utility. | Anish Akhilesh Gupta | Critical |  | Open | Critical
10 | Issue | HSTS and X-Frame-Options headers found missing on the target during Nmap/Nikto scanning. | Site is more exposed to protocol-downgrade and clickjacking risks than it should be. | Logged as a High/Medium finding with a specific suggested patch in the Findings Document. | Anish Akhilesh Gupta | High |  | Open | High
11 | Dependency | Guidance and feedback from the Project Manager on scope, templates and the 'List of Deliverables'. | Wrong format or missing content if guidance is not received in time. | Raised queries early; followed the provided templates exactly. | Harshada Topale | Moderate |  | Open | Moderate
12 | Dependency | Continuous availability of the hosted giftacareer.in testing instance. | Scans cannot complete if the target is down. | Scheduled scans in a single focused session once connectivity was confirmed. | Anish Akhilesh Gupta | Moderate |  | Closed | Low
13 | Dependency | Stable internet connection throughout scanning (ZAP spidering and active scan can take 20-60 minutes). | Delays or incomplete scans if the connection drops. | Ran long scans on a stable connection and kept raw output files as evidence. | Anish Akhilesh Gupta | Moderate |  | Closed | Negligible
14
15
16
17
18
19
20
21
22
23
24