## Sheet1
IAC REQUIREMENT ELICITATION QUESTIONNAIRE
Intern Name: | Anish Akhilesh Gupta (Intern ID: IP-11783)
Selected Domain: | Cyber Security
Domain Problem/Project name: | Web Service Open to Malicious Attacks
Meeting Date & Time | No project-specific requirement meeting was conducted; requirements were derived from the Problem Statement document.
Meeting Venue/ Link: | Weekly general internship meeting conducted through Zoom (no separate project-specific meeting link).
Stakeholders Present in the Meeting: | General internship coordinators and interns (weekly meeting); no dedicated stakeholder meeting held for this project specifically.
This questionnaire is to be used by the consultant to gather requirements from the client
QUESTIONS | ANSWERS
General Inquiry
What do you hope to accomplish with the proposed project? | Available in Problem Statement (Relevance): ensuring the company's web assets, including giftacareer.in, are adequately protected from malicious motives ranging from service disruption to data theft.
How do the project/system’s goals map to the department goals or needs? | The audit supports the company's goal of maintaining a secure public-facing web presence and gives concrete, prioritised findings that management can act on.
What will the project accomplish that is not currently accomplished manually or with other projects/software? | Previously the site's security posture was not independently verified by an intern-led audit. This project adds a documented, tool-based assessment covering network, server and application layers.
Are there other projects/systems with which this project/system will interface? | No external system integration is required; the only interface is to the hosted instance of giftacareer.in itself over standard HTTP/HTTPS.
Is there any existing project/system documentation? | The Problem Statement (with its audit checklist) is the only document provided; no prior audit report existed to reference.
Current Needs and Problems
What department/business requirements will this project/system address? | Available in Problem Statement (Relevance): protecting company web assets from malicious motives ranging from service disruption to data theft.
Is any of this data currently captured in any other project/system?  Is the data and/or functionality shared by others? | Not specified; assumed the site has not undergone a formal third-party security audit before.
What problems should this project/system solve? | Available in Problem Statement (Background): cybersecurity threats and cyber-attacks pose growing financial and reputational risk.
Do you have to do things manually that you would like to automate | Yes - port/service scanning, header checks and vulnerability-signature matching are best automated (Nmap, Nikto, ZAP); manual verification is used only to confirm automated findings.
Do you have performance problems that need to change? | Not specified; scans were run with default tool timings and, where relevant, time-capped to fit the internship deadline.
Do you have functional limitations that you’d like to change? | The main limitation addressed is the lack of an independent, documented check of headers, TLS configuration, HTTP methods and common web vulnerabilities.
What will this project/system do that is entirely new? | Combined network (Nmap), server (Nikto) and application (ZAP) scanning in one coordinated audit, with a single consolidated findings report.
Criteria for success
What is most important for success of the project? | Success means every audit checklist point in the Problem Statement is addressed, with no service disruption caused, and with clear, actionable findings delivered on time.
What are the training considerations? | No new training is required; the steganography deliverable and the Findings Document are the required training/learning artefacts.
What resources might be needed (budget, staff, etc) | No budget. Only open-source tools (Nmap, Nikto, OWASP ZAP, Python/Pillow). Intern effort of about 30 hours; laptop and internet connection.
Are there any dependencies on other project/system in completing the project/system? | Depends on Project Manager guidance, the Problem Statement, and continued availability of the hosted test instance.
Are there resource constraints in maintaining the project/system? | Minimal - the audit itself does not need ongoing maintenance; only the report and recommendations are maintained going forward by Cloud Counselage.
Do you have the in-house expertise we need? | The intern has working knowledge of networking, Linux, Python and basic web technologies; tool usage was learned from official documentation during the project.
Are there technical constraints to developing this project/system? | Scope limited strictly to the hosted instance; no brute-force or DoS attacks; limited time; the target's WAF may hide some deeper findings.
What needs to happen to make this project/system successful? | A complete, well-evidenced Findings Document with no scope violations, submitted by the 17-Oct-2026 deadline.
Finding Stakeholders
Who are the key stakeholders and users? | Cloud Counselage management (Sponsor and asset owner), Project Manager, and the intern/tester.
Do their goals differ? If so, how? | Yes - management wants assurance with no business disruption; the tester wants a thorough, efficient audit within the time available.
Who uses the system? | The intern (tester) directly; Cloud Counselage management indirectly, as recipients of the Findings Document.
Who installs the system? | The intern installs and runs the tools (Kali Linux / native installs) on their own machine; no deployment onto company infrastructure is required.
Who trains people to use the system? | No formal training is required for this one-off audit; the Findings Document itself documents the process for future reference.
Who fixes the system? | The intern, for the duration of the project; the Project Manager afterwards for review.
Who maintains the system? | The intern during testing; the Cloud Counselage security/IT owner afterwards, if remediation is undertaken.
Who creates, updates, deletes information in the system? | The intern runs scans and records findings; the asset owner (Cloud Counselage) authorises scope and later decides on remediation.
What other systems interface with the system? | No other system interfaces; the audit only interacts with the single authorised hosted instance over HTTP/HTTPS.
Who gets information from this system? | The intern (direct user of the tools) and Cloud Counselage management/Project Manager (consumers of the report).
Who provides information to the system? | The target website provides the data being analysed; the intern records findings; no member/personal data is collected in this project.
Are there are others they believe should be involved in the process of identifying the project requirements? | The Project Manager should review scope boundaries and the final Findings Document before it is shared further.
Whats the process
What is the purpose of this process? | To determine whether giftacareer.in is vulnerable to malicious attacks and to document any issues found along with fixes.
What triggers this process to start? | The assigned Problem Statement initiates the audit; each scan run is a sub-process within it.
Who is responsible to perform this process? | The intern, for running tools and documenting results; the Project Manager, for reviewing scope and deliverables.
How does this process work today? | Assumed to be an unaudited or infrequently audited public web asset prior to this project.
What is the end result or output of this process? | A clear picture of the site's security posture: what is protected well, what is missing, and what should be fixed.
Is there a system that supports this process today? | Not specified; no existing audit/report was provided as a starting point.
If there is a system, are you able to show us how this system works? | N.A. - no existing audit report or system documentation was supplied.
If there is a system, are you able to provide us with some screen shots from this system? | N.A. - no prior audit screenshots were provided.
If there is a system, are you able to refer us to where we can find the user guide for this system? | The Problem Statement document itself, including its audit checklist and list of deliverables.
Reports
Do you currently have any existing operational reports which help you manage this team? | Not specified by the Problem Statement; the Findings Document itself serves as the operational report.
Are you able to tell us about your most important reports? | Nmap scan outputs, Nikto scan output, and the OWASP ZAP exported report, consolidated into one Findings Document.
Which systems produce your reports for you? | Terminal output files (.txt/.xml/.gnmap for Nmap, .txt/.html for Nikto) and the ZAP HTML/PDF export.
How often to you receive these reports? | One-time, at the end of the authorised testing window (before the Findings Document is submitted).
Are you able to share some examples of these reports with me/ us? | Sample outputs and key findings are included as evidence in the Findings Document and demonstrated in the project video.
Tell us about some of your reporting requirements. What would you really like to see produced as a report? Why? | Missing security headers, weak TLS configuration, risky HTTP methods, exposed backups/admin panels and known CVEs - each flagged by severity.
Discuss the content, frequency, audience and layout of the report at a high level. | Content: finding, affected URL/port, severity, evidence, suggested fix; frequency: one-time per audit; audience: Project Manager and Cloud Counselage management; layout: a findings table grouped by tool/category.
Identifying use cases
What functions will the users want from the system? | Run Nmap recon and vulnerability scripts; run a full Nikto scan; run an OWASP ZAP spider and active scan; record findings; build and test the steganography utility.
Does the system store information? | No persistent data store is created by the audit itself; only output log files and the final report are produced and retained.
Do the users need to create, update, or delete information? | N.A. - the audit is read-only with respect to the target; it does not create, update or delete target data.
Does the system need to notify a user about changes in an internal state? | The tester sees terminal output and ZAP alerts in real time; no end-user-facing notifications exist for this audit.
Are there any external events the system must know about? | A scan returning no response, a WAF block, or an unexpected status code are flagged for manual review.
What is the user’s overall job? | The intern runs each tool, reviews raw output, and extracts/records the relevant findings into the report.
What problems have the users had in the past? | Typical problems are noisy/irrelevant output needing filtering, and scans being partially blocked by a WAF.
What steps are manual today? | Manual review and cross-referencing between the three tools' outputs is used to confirm genuine findings and reduce false positives.